## Sheet1
| ¦¦ JOB COMPLIANCE CHECKLIST (QC) ¦¦ |  |  | NOTE :
Customer Name : Christine Hill & Ashley Hill
Correct Address : 5 Elm Cres, Emerald VIC 3782
Checked By : Ryan Culin
Installation Date : 9/06/2026
Job Details : 26.0 X JKM510N-51QL6-DV , 1.0 X FOXESS inverter KH10, 1.0 X FOXESS EQ4800-L7 ( 32.61kWh )
S.No. | CheckList | Yes/No | Remarks | What to verify as per Agreement
1 | Signed Agreement | Y | Refer to Signed Agreement New.pdf | Signed , no over-writing from pen
2 | Deposit | Y | Refer to Deposit.jpg | Amount, Name, successful status
3 | Meter Photo/Switchboard | Y | Refer to Meter box.png | Should have meter and switches / switchboard
4 | Phase and upgrade | Y | Refer to phase and upgrade approval.jpg | Phase should match with Agreement, notify if upgrade requires
5 | Roof Pic/House Pic | Y | Refer to house pic.jpeg | Should have proper house picture
6 | Storey and Roof Type | Y | Refer to house pic.jpeg | Stories and roof type should match
7 | Electricity Bill(All Pages) | Y | Refer to Ebill.pdf | Should have 1st page
8 | Rate Notice | Y | Refer to Rates + DL.jpeg | Name / Address should match
9 | Meter Approval | Y | Refer to Meter approval.pdf + Meter application.pdf | Address / product Should match
10 | Roof Layout approved by Sam/Ryan/Sunjeet | Y | Refer to Layout approval.jpg + Layout.word | Should mention "ok to send", any suggestion should be matched in agreement, layout file should have same panel model/qty
11 | Inverter Location pic approved by Sam/Sunjeet/Ryan | Y | Refer to phase and upgrade approval.jpg | Should mention "ok for location"
12 | Tilt frame/Clip Lock | N | Refer to house pic.jpeg | Check only when it is tin/flat roof
13 | Scissor Lift required or not | N | Refer to house pic.jpeg | If Double story or more, difficult to access rear roof, too high
14 | Welcome Email/Invoice/RL/Inverter Location/Fact sheet | Y | Refer to Welcome email.jpg | Check subject, email, name, product information as per agreement
17 | Solar VIC Loan and Rebate Approved | Y | Refer to Solar VIC approval.jpg | Check name , approval status, amount
18 | Finance Approved (Brighte/Plenti) | Y | Refer to Signed Agreement New.pdf | Check name , approval status, amount
19 | Export Approved | Y | Refer to Meter approval.pdf | Approved export limit , notify if <5kW approved when single phase
20 | Type of Installation ? | Y | Refer to Meter box.png | Check if no existing battery switch in swithcboard and if yes, notify
21 | Job checked by Accounts | Y | Refer to Accounts approval.pdf | Customer name, installer, product, warehouse, story and Approval status
22 | Customer informed installation date both on phone and email | Y | Refer to confirmation email.pdf | Check booking date, name and email matches with agreement
23 | Wi-Fi availability | Y | Refer to confirmation email.pdf | If nothing mention for wifi, it means ok to proceed as cx has it
26 | Updated signed agreement from customer if change in panel number and model | Y | Refer to Signed Agreement New.pdf | Signed , no over-writing from pen
27 | Updated signed agreement from customer if change in inverter number and model | Y | Refer to Signed Agreement New.pdf | Signed , no over-writing from pen
28 | Sent customer updated Invoice, roof layout and inverter location if any change then original signed agreement before installation | Y | Refer to confirmation email.pdf | Check name and email
29 | Raise PO to respective Suppliers (check Export control required or not) | Y | Refer to PO email.pdf | Check if PO send to correct warehouse and their email , state and Product as per agreement
30 | Double check SO against Original Signed Agreement | Y | Refer to packing slip.pdf | Verify state, product against agreement
31 | Double check Packing Slip against Original Signed Agreement
i | Panel model matches with signed agreement | Y | Refer to packing slip.pdf | Confirm yes if matches as per Agreement
| Panel model in signed agreement |  | Refer to Signed Agreement New.pdf | Write Panel model
| Panel model in packing slip |  | Refer to packing slip.pdf | Write Panel model
ii | Total number of panels ordered matches with signed agreement |  | Refer to packing slip.pdf | Verify state, panels against agreement (make , model, qty )
iii | Inverter model ordered matches with signed agreement | Y | Refer to packing slip.pdf | Confirm yes if matches as per Agreement
| Inverter model in signed agreement |  | Refer to Signed Agreement New.pdf | Write inverter model
| Inverter model in packing slip |  | Refer to packing slip.pdf | Write inverter model
iv | Battery model matches with signed agreement | Y | Refer to packing slip.pdf | Confirm yes if matches as per Agreement
| Battery model in signed agreement |  | Refer to Signed Agreement New.pdf | Write Battery model
| Battery model in Packing slip |  | Refer to packing slip.pdf | Write Battery model
v | Tile kit/Tin Kit/Flat roof | Y | Refer to packing slip.pdf | Verify roof kit against agreement
vi | Export Control Device / Smart Meter | Y | Refer to packing slip.pdf | Verify item against agreement
vii | Electrical Kits | Y | Refer to packing slip.pdf | By default given by warehouse
viii | Optimizers | Y | Refer to packing slip.pdf | Verify item qty against agreement
ix | Tilt Frame/ Clip Lock | Y | Refer to packing slip.pdf | Verify item against agreement when tin/flat roof
32 | Organise Delivery of material if required | Y | Refer to delivery email.pdf | Check product, customer details, correct packing slip number given
33 | Inform installer installation date both phone and email | Y | Refer to Job detail.pdf + WO email.pdf | Installation date, installer approved by account, charges should be as mentioned in accounts approval.pdf
35 | Raise WO for Installer | Y | Refer to WO email.pdf | customer details, product info, backup info, wifi set up and QR scan line should be mentioned,
36 | Create STC in Green Deal/Bridgeselect | Y | Refer to STC creation.png | Customer details and accounts approved installer, product info, installation date
CEC Approved Battery
i | Battery Approved Date | Y | Refer to CEC battery approval.jpg | Write approval date
ii | Battery Expiration Date | Y | Refer to CEC battery approval.jpg | Write expiry date, notify if it is close to the booking date
CEC Approved Battery
i | Electrician License Expiration Date | Y |  | Verify installer name and expiry date should be after booking date
ii | SAA Expiration date | Y |  | Verify installer name and expiry date should be after booking date